## Summary
ITEM | DESCRIPTION | TOTAL £
1 | Preliminaries
1.01 | Preliminaries
2 | Asbestos
2.01 | Asbestos Survey
3 | Communal External
3.01 | Hardstanding
4 | External
4.01 | Scaffold
4.02 | Cladding
4.03 | External Doors
4.04 | Roof Covering
5 | Internal
5.01 | Remodelling Works
5.02 | Windows
5.03 | Internal Doors
5.04 | Wall & Ceiling Works
5.05 | Flooring
5.06 | Cleaning
6 | M&E
6.01 | M&E Works
7 | Contingency
7.01 | Allow a contingency sum to allow for any unforeseen works @7.5%
7.02 | Contractor Overheads & Profits
TOTAL COST

## 1.0 - Prelims
1 | PRELIMINARIES | QTY | UNIT | RATE | TOTAL £
1.01 | Preliminaries Location: All |  | weeks
- | Prior to tender submission the contractor should visit site to ascertain and familiarize the full extent and complexity of the works. The contractor is expected to determine all quantities and dimensions and make their own notes during the site visit as claims for additional costs will not be considered. |  | -
- | The contractor must price each and every individual item contained within the Preliminaries (where applicable). |  | -
- | This Specification is to be read in conjunction with the tender drawings as listed in the Drawing Register. |  | -
- | The contractor shall include for all necessary scaffolding, access/hoisting equipment, plant, skips etc. as required for the safe carrying out of the works in accordance with health and safety requirements. |  | -
- | The contractor is responsible for obtaining all necessary service plans, including gas, electric, water mains, sewers and drainage and telecommunications as necessary to complete the works. |  | -
- | All works to be carried out in a competent and workmanlike manner. The site shall be kept clean and tidy at all times. |  | -
- | The Contractor is to allow for all removal, reinstatement and completion of services works as required in the Mechanical and Electrical Services section including all integration and sequencing of these works. |  | -
- | Contractor is to maintain fire integrity and detection at all time as a consequence of the works. Detection and sounders in the areas of work are to be maintained and connected to the main system. |  | -
- | Contractor to carry out pre-start photographic survey of all areas prior to commencement of work. The client will not be held responsible for cost associated with complaints & defects if photographic evidence is not available. |  | -
- | The contractor is to allow for all necessary making good to any existing surfaces including walls, floors, ceilings, fittings and fixtures etc. disturbed due to the works specified hereunder. |  | -
- | Contractors are advised that copy invoices will be required by the Contract Administrator in support of any, and all, expenditure incurred in execution of works described under the heading "Provisional Sums". The Contractor must always relay back to the Contract Administrator for approval the cost of any variation or instruction. |  | -
- | Allow for the removal of waste, spoil and debris as it accumulates during the programme of works. No debris should be left to accumulate outside or inside of the property. Any debris left outside must be removed at the end of the working day to remove the potential risk of arson. |  | -
- | The contractor must make allowance for obtaining any necessary Statutory Approvals where not already provided. Building Regulation Approval and Planning Permissions have already been received. |  | -
- | The Contractor shall provide all permanent and temporary notices and labels required by the local authorities or statutory requirements. |  | -
- | It is the contractor’s responsibility to programme any statutory holidays in their programme. |  | -
- | The Contractor shall submit an outline programme with this tender. The contractor will carry out the works with due diligence and the programme of works will be evaluated to assess this. |  | -
- | The Contractor is to allow for all sequencing and integration of work clauses for the proper execution of the works including full co-ordination of all subcontractors. |  | -
- | Welfare Facilities: The project will be notifiable under the Construction Design and Management Regulations 2015. The successful contractor will be appointed as Principal Contractor and will be required to undertake all the duties required of a Principal Contractor under the CDM 2015 Regulations. The contractor is to allow for full compliance with the CDM 2015 Regulations. |  | -
- | The contractor will provide welfare facilities as required by the CDM regulations. These facilities will take the form of a toilet in the compound, office and canteen facilities within the site which will have hot & cold running water and power supply via generator. |  | -
- | Contractor to agree with Karbon Homes where car parking is allow to the area. Consideration must be given to the access and parking for the adjacent school. |  | -
- | Site Security: Whilst pricing the works the contractor shall include for all the necessary security fencing, storage containers and other measures on and around the site for the duration of the contract. |  | -
- | Claims for loss of materials, equipment or delays in the completion date will not be considered. Allow third party liability insurance during the programme of works. |  | -
- | Allowance for Site Setup |  | -
- | Allowance for Site Management |  | -
- | Allowance for Site Waste Management (clearance, storage and removal) |  | -
- | Allowance for Plant Machinery and Equipment |  | -
Section Total

## 2.0 - Asbestos
2 | ASBESTOS | QTY | UNIT | RATE | TOTAL £
2.01 | Asbestos Survey Location: All | 1 | item
- | Allow to undertake refurbishment and demolition asbestos surveys to the areas affected by the works. Survey findings and reports to be issued to the CDM Principal Designer.
2.02 | Asbestos Removal Location: All | 1 | PC Sum |  | 1000
- | Allow for a PC Sum of £1000 for the removal of any asbestos material from the property prior to the start of the works.
Section Total

## 3.00 - Hardstand
3 | COMMUNAL EXTERNAL | QTY | UNIT | RATE | TOTAL £
info | The building is Grade II* Listed, therefore any works are to be as existing.
3.01 | Hardstanding Location: All | 1 | item
- | Clean down existing concrete paving to externals and treat for moss removal. Dispose of arisings.
Section Total

## 4.01 - Scaf
4.01 | SCAFFOLD | QTY | UNIT | RATE | TOTAL £
4.01.1 | Scaffold Location: All elevations | 15 | lm
- | Contractor to allow for obtaining all necessary permits from the Local Authority for the erection of scaffold necessary to carry out the works.
- | Contractor is to design and erect full independent scaffold to the property to allow for all external works detailed within this document. Include for lifts, chutes, ladders, beams etc as required. Full designs to be sent to Principle Designer before work commences. The scaffolding is to comply with the requirements of the Construction (Health, Safety and Welfare Regulations) 1996, the Work at Heights Regulations 2005, British Standards BS1139, BS2482:2009, BS4074:2000 and BS EN 12811-1:2003.
- | All scaffold tubes must be galvanized and comply with BS EN 39:2001. All scaffold boards are to be secured to prevent displacement. All scaffold fittings must comply with current UK industry standards. All masonry anchors that are used for the installation of scaffold ties must be tested in accordance with NASC TG4 and the records of the tie test must be forwarded to the Contract Administrator.
- | The Scaffolding company must be full and regulated members of the National Access and Scaffolding Confederation (NASC). The scaffolding company must employ a minimum of one CISRS qualified Advanced Scaffolder on the project. Management, supervision and operatives employed by the scaffolding company must have the received the relevant training on TG20 and SG4. As the scaffolding, will be a Designed Scaffold, the company must employ or have access to competent scaffold designers and the scaffold design and calculations forwarded to the Contract Administrator prior to commencement of work on site.
- | The scaffolding is to be inspected on a weekly basis by either the scaffolding contractor or a competent person employed by the Principal Contractor and the inspections recorded in a scaffold register available on site for viewing by the CA or on a Scaftag.
- | The Principal Contractor is to allow for the provision of calculations to be forwarded to the Contract Administrator for any Design Scaffolding required in order to facilitate the contract. Ladders to first working platform to be removed or locked at the end of each working day to prevent access to the scaffolding by any unauthorised persons.
- | Allow for brick guards, etc to prevent materials falling. Allow for suitable protection of the scaffolding standards to prevent accidental collision.
Section Total

## 4.02 - Clad
4.02 | CLADDING | QTY | UNIT | RATE | TOTAL £
info | The building is Grade II* Listed, therefore any works are to be as existing.
4.02.01 | Timber Cladding - Redecoration Location All Elevations
- | Redecorate existing timber cladding. Allow to use paints and colours as described in the Byker Estate Heritage Partnership Agreement (HPA). All elevations to be Byker Green (Jotun 02). | 35 | m²
4.02.02 | Timber Cladding - Repairs Location: General | 1 | PC Sum
- | Allow a PC Sum of £500 for timber cladding repairs where found necessary. Timber profile to match existing. |  | -

## 4.03 - Doors
4.03 | EXTERNAL DOORS | QTY | UNIT | RATE | TOTAL £
info | The building is Grade II* Listed, therefore any works are to be as existing.
4.03.01 | Main Entrance Door Location: South Elevation | 1 | nr
- | Existing door and frame to be removed and disposed offsite with care to avoid unnecessary damage to the structure of the building and its finishes, and without permitting any subsidence of the superstructure during or after the installation procedure. |  | -
- | Contractor to supply and install new timber Byker Style external entrance door, with double glazed vision panel. Door to be as per specification within Byker Heritage Partnership Agreement below. |  | -
- | The door will be site measured and manufactured to suit the existing opening with level thresh. Designs to be approved by CA prior to ordering. Contractor to make good any damage around existing plaster opening. |  | -
- | Heritage Partnership Agreement door specification as follows: |  | -
- | Front and rear door sets Byker Estate: • Factory Double Glazed and Factory Finished Doors and frames. |  | -
- | Manufacturer: • See HPA approved Manufacturers table Page 228 • To be supplied by Manufacturer holding ‘Secured by Design’ License, or • Provisional or Full Member of BM Trada ‘Q-Mark Enhanced Security Doorsets and Windows Manufacturers Scheme. |  | -
- | Recommended minimum warranties: • Rot & Fungal Attack - 30 Years • Glazing System Failure - 10 Years • Manufacturing Defects - 10 Years • Ironmongery - 5 Years • Factory Applied Coatings - 8 Years |  | -
- | Construction: • 44mm total thickness. 4mm hardwood WPB graded plywood veneered laminate on solid timber / insulating flaxboard / laminated block core. Raised mouldings to both sides of all doors. Specification is for guidance only. An equal and approved Specification from an approved supplier from the list provided is acceptable. |  | -
- | Performance: • 24mm obscure double glazed units if required by style. • External pane to be 6.4mm laminated double-sided glazing tape/silicone bedded. Glazing beads to be fixed at 150mm ctrs. and bedded in silicone. |  | -
- | Frame: • Either Hardwood (Sapele) or softwood (Redwood). Decorated to HPA requirements. |  | -
- | Ironmongery: To PAS 23 and PAS 24. • Description : • FRONT DOOR - 3 No. specialist hinges (incorporating hinge bolts). *Multi-locking espagnolette system operated by key locking lever handles, low cill / threshold (to Part M ), letter plate ref. ‘Paddock Fabrications’ P209 Postmaster – SAA, SAA knocker, SAA nameplate, 180 d. eye viewer, door chain, SAA numerals, internal letter plate cover. |  | -
- | Ironmongery Specification: • *Locking Mechanism to be‘Fullex’ SL-16 Crimebeater Multi-bolt locking system, ‘Hoppe’ Tokyo handle (SAA finish) (CRBHAN0005), Solid spindle (SL97/ACO248),Cylinder(25603 30-10-30) SAA anti drill:M5 x 55 fixing screw with ‘Fullex’ Crimebeater Cylinder guard(70016) |  | -
- | Threshold: • ‘Stormguard’ Proline AM3 (inover opening), AM5 (outover opening) or equal and approved (to meet Part M, Building Regs.) |  | -
- | Sections: • Design of doors to ensure the size of top rails and styles are a minimum of 100mm and a maximum of 150mm. |  | -
- | Fixing: • Door frames fixed at max. 600mm ctrs, 300mm from each corner. |  | -
- | Weather-stripping: • Schlegal Aquamac 21 or equal and approved. |  | -
4.03.02 | Fire Exit Door - Side Location: North East Elevation | 1 | nr
- | Allow for lowering the existing door and frame level with internal floor level and securely fix to walls. |  | -
| Supply and fit insulated spandrel panel to infill gap left above door frame and wall. |  | -
| Allow to seal around door to new location and making good the walls. |  | -
| Supply and fit level threshold to door. |  | -
4.03.03 | Rear Door Infill Location: Rear exit door | 1 | Nr
- | Allow to overhaul existing door, including any necessary timber repairs found. Screw shut from inside. Decorate door to match existing colours. |  | -
- | Block up internal side of door and plaster to leave flush with existing internal wall finish. |  | -
Section Total

## 4.04 - Roof
4.04 | ROOF | QTY | UNIT | RATE | TOTAL £
info | The building is Grade II* Listed, therefore any works are to be as existing. |  | -
4.04.01 | Roof Covering Location: Front Extension | 32 | m2
- | Allow to clean and prepare the existing profiled metal roof sheets to the main roof and to front extension. Include to treat any corroded metal with Giromax Edgecoat and Giromax Roofcoat or similar to manufactures recommendations. Colour to be Wedgewood Blue, or Cobalt Blue/Tartan Blue (BS 18E53) to local authority approval. |  | -
4.04.02 | Valley Guttering Location: Front Extension | 1 | PC Sum |  | 500
- | Allow a PC Sum for cleaning out, inspecting and repairing box guttering as necessary. Include to treat any corroded metalwork and decorate area to match the existing to local authority approval. |  | -
4.04.03 | Install New Sun Pipes Location: See Storm Tempest Drawing | 2 | nr
- | Supply and install 2nr. Monodraught Diamond Dome Orion Sunpipes in pitched gallery configuration. Design to include stainless steel bezel and curved diffuser panel. Allow to include alterations to existing metal sheet roof covering and new flashing where required. Units to be installed to rear roof pitch as per the Storm Tempest proposed drawing. All to approval by local authority conservation officer. Make good ceiling around internal fittings. |  | -
Section Total

## 5.01 - Remodel
5.01 | REMODELLING WORKS | QTY | UNIT | RATE | TOTAL £
5.01.01 | Stripping Out - Plumbing Location: General | 1 | item
- | Allow to isolate all plumbing as required for the works. Allow to reconnect on completion and commission where required. |  | -
5.01.02 | Stripping Out - Exisitng Location: General | 1 | item
- | Allow to remove items currently stored on site and dispose. Strip out all fixture, fittings, furniture and sink including tiling and dispose from site. Strip out existing desks, shelves etc. and dispose from site. |  | -
5.01.03 | Stripping Out - W/C Location: Existing W/C | 2 | nr
- | Strip out existing W/C, WHB, including all sanitary ware, wall tiling, handles, timber boxings and dispose from site. |  | -
5.01.04 | New W/C - Install Location: See Storm Tempest Drawing
- | Allow to take down existing partition walls to locations shown on drawings and dispose off site. | 5 | lm
- | Allow to patch repair existing floor finishes where walls removed and leave level and flush with existing floors. | 5 | lm
- | Allow to patch repair existing ceiling and wall finishes where walls removed and leave flush with existing floors. | 13 | lm
- | Construct new timber framed partition walls to locations shown in drawings, with plaster board over and skim finish. Allow to include mineral wool insulation to the walls for sound attenuation. | 20 | m2
- | Supply and fit timber skirting to both sides of the walls. Decorate with white gloss paint as per manufacturers instructions. | 22 | lm
- | Supply and install new flush plywood timber door, frame and architraves, including 1.5 hinges, lever door handle, lock and thumb turn. | 2 | nr
- | Supply and fit new standard Doc M pack with WC, WHB, 2no coat hooks, 1no. Mirror and grab rails, paper towel dispenser and electric fan hand drier, as per Storm Tempest Proposed Layout Drawing. | 1 | nr
- | Construct new timber framed boxing with plywood board covering, to exposed pipework. Allow to screw fit plywood with plastic caps over screw heads, to allow for removal for maintenance. | 2 | m2
5.01.05 | New W/C - Tiling Location: New W/C | 0.5 | m2
| Supply and fit new white 150x150mm white ceramic tiling to behind WHB. Include for white trims to tops and sides. Apply sealant between WHB and tiling. |  | -
5.01.06 | Stripping Out - Kitchen Location: Existing Kitchen
- | Strip out existing kitchen units, worktops and sink and dispose off site. Carefully strip out existing instantaneous water heater and set aside for later reinstall. | 3 | lm
- | Cap off and strip out existing kitchen supply and waste pipes and dispose off site. Make good wall and floors where necessary. |  | item
Section Total

## 5.02 - Windows
5.02 | WINDOWS | QTY | UNIT | RATE | TOTAL £
The building is Grade II* Listed, therefore any works are to be as existing.
5.02.01 | Timber Window Frame Repairs Location: All windows | 1 | item
- | Inspect all existing timber windows and carry out necessary localised repairs to ensure weather tight. Sand and prepare window frames for redecoration. All materials and methods to be compatible with existing joinery and appropriate for use on heritage buildings to approval of Local Authority Conservation Officer. |  | -
5.02.02 | Double Glazing Repairs Location: North East Elevation | 1 | item
- | Carefully remove and dispose of existing failed (blown) double glazed unit from window frame. Measure and supply new double glazed sealed unit to match existing in size, thickness, glazing specification, and appearance. Install new unit using appropriate glazing beads, setting blocks, and sealants to ensure a weather-tight and secure fit. Ensure all works are carried out without damage to surrounding frame or finishes. |  | -
5.02.03 | Timber Window Decoration Location: All Windows | 6 | nr
- | Redecorate existing timber window frames internally and externally. Allow to use paints and colours as described in the Byker Estate Heritage Partnership Agreement (HPA). All frames to be Red Umbra (Jotun 2219).
5.02.04 | Window Film Location: Rear and side windows | 2 | m2
- | Supply and fit opaque window film to inside of windows for privacy. Window film design/pattern to be agreed with CA.
5.02.05 | New Security Roller Shutters Location: Front Windows | 2 | Nr
- | Supply and fit new aluminium roller shutter, with perforated slats and electric operation, to the internal side of the front elevation and side elevation windows, as shown on Storm Tempest drawings, installed to manufactures instructions. Shutters to be galvanised finish. Electric operation to be controlled from front door. |  | -
5.02.06 | New Security Metal Bars Location: Small rear and side windows | 2 | Nr
- | Supply and fit new steel security bars, fitted internally to small rear window to WC and small side window to changing area. Fit securely to wall as per manufacturers recommendations. Decorate to match adjacent walls. |  | -
Section Total

## 5.03 - Walls & Ceilings
5.03 | WALL & CEILING WORKS | QTY | UNIT | RATE | TOTAL £
5.03.01 | Replastering Location: All Walls & Ceiling | 180 | m2
- | Allow to prepare all walls and ceilings throughout the whole building. Allow to apply skim plaster to all walls, partitions and ceilings. |  | -
5.03.02 | Decoration Location: All Walls & Ceiling | 180 | m2
- | Decorate all walls and ceilings with 2 coats of emulsion paint to clients approval. |  | -
5.03.03 | Fire Stopping Location: Understairs Cupboard | 0.5 | m2
Supply and install fire-rated ablative coated mineral fibre batts to fully seal the void above the head of the door in the understairs cupboard. Batts to be cut and friction-fitted to form a tight, continuous barrier. Apply intumescent sealant to all perimeter joints and service penetrations around the batts to ensure a fully fire-stopped installation. Sealant to be compatible with both the batts and surrounding materials, and installed in accordance with manufacturer’s instructions. All materials to be third-party certified and installed by competent operatives.
Section Total

## 5.05 - Floor
5.05 | FLOORING | QTY | UNIT | RATE | TOTAL £
5.05.01 | New Floor Coverings Location: All Areas | 69 | m²
- | Take up existing floor coverings and dispose of. |  | -
- | Allow to prepare floor finish ready for new coverings. |  | -
- | Supply and fit Altro Stronghold 30 to all areas of the building to manufacturers recommendsation. Colour/pattern to clients approval. Allow to mastic seal perimeter and weld all joints where required to manufacturers recommendations. |  | -
Section Total

## 5.06 - Clean
5.06 | CLEANING | QTY | UNIT | RATE | TOTAL £
5.06.01 | Clean Down Surfaces Location: All Surfaces | 1 | item
- | On completion, clean down all surfaces, floors, walls, windows etc. |  | -
Section Total

## 6.01- M&E Works
6.01 | M&E WORKS | QTY | UNIT | RATE | TOTAL £
6.01.01 | Electrical Rewire Location: General | 1 | item
- | Allow to remove existing electrical system, including lighting and dispose off site. Supply and fit new electrical system to IEE 18th Edition. Liaise with client for socket and lighting locations and requirements. Allow to chase cables into walls and make good surfaces. New lighting to be LED and to provide suitable illumination for the use of the rooms, with consultation with the client. Provide all commissioning certificates. |  | -
- | Allow to include at least 14 double sockets in locations to be agreed.
6.01.02 | Mechanical Ventilation Location: New W/C | 1 | nr
- | Supply and fit mechanical humidistat controlled extract fan to WC. Allow to core drill through external side wall to provide ducting. Allow to provide electrical connection, including isolating switched fuse spur located over door within changing room. |  | -
6.01.03 | Instantaneous Water Heater Location: Under Kitchen Sink | 1 | item
- | Reinstall previously set aside instantaneous water heater, including all necessary plumbing and electrical connections, pressure relief components and commissioning. |  | -
6.01.04 | New Security Roller Shutter Location: Front Door and Side fire exit door | 2 | item
- | Allow to carry out all works required to provide powered roller shutters with the necessary electrical power supply. Where necessary, allow for surface mouted conduit from consumer unit to required locations. Allow to comission electric system. |  | -
6.01.05 | Bakery Fixtures & Fittings - Oven | 1 | item
- | Supply and install Blue Seal Turbofan Convection Oven. Model no. E32D4. |  | -
6.01.06 | Bakery Fixtures & Fittings - Ventilation | 1 | item
- | Supply and install Lincat Britannia SmartVent Extract System. Model no. SV1216CV. Location: Rear wall as shown on drawings. |  | -
6.01.07 | Fire Detection System Location: General | 1 | item
- | Allow to protect existing fire detection system during the works. Allow to test and commission fire detection system on completion of works. |  | -
6.01.08 | Security Alarm System Location: General | 1 | item
| Allow a PC Sum of £1,000 for the supply and fit of a new security alarm system, including control panel, room sensors, door and window sensors. Allow to provide commissioning certification. |  | -
6.01.09 | Comissioning Location: General | 1 | Item
- | Allow to test and commission all M&E services within building. Provide all necessary certification. |  | -
Section Total

## 7.01
7.01 | CONTINGENCY | QTY | UNIT | RATE | TOTAL £
7.01.1 | Contingency | 1 | Item
- | Contingency sum of 7.5% to allow for any unforeseen works, to be used in whole or part, only upon written instructions from the Contract Administrator.
Section Total

## 7.02
7.02 | OVERHEADS & PROFIT | QTY | UNIT | RATE | TOTAL £
7.02.1 | Contractor Overheads & Profits |  | Item
- | Contractors Profit |  | Item
- | Contractors Overheads |  | Item
Section Total